## Slide 1
9th July 2020
CTI-CFF
Regional Secretariat/Dr. Sada
Introduction to
Monitoring & Evaluation: Indicators, Targets, Milestones, Benchmarks Outcomes & Outputs.
Photo by: James Morgan

## Slide 2: Background
This presentation contains basic definitions of key concepts used in monitoring and evaluation.
Definitions are illustrated with practical examples regarding each concept.
These key concepts are monitoring, evaluation, indicators, targets, milestones, benchmarks, outcomes and outputs.
At the end of presentation you will understand the key concepts about M&E. We encourage you to ask questions.

## Slide 3
Monitoring

## Slide 4: Definition of Monitoring
Word monitoring is taken from Latin word ‘Monere’, that means to warn or to remind (Kaushik, 1995).
Monitoring is the periodic tracking of any activity’s progress by systematically gathering and analyzing data and information that measures progress toward achieving program objectives. It is used to track changes in program outputs and performance over time. It provides regular feedback and early indications of progress (or lack of progress).
Its purpose is to inform management and stakeholders to make timely and informed decisions regarding the effectiveness of programs and the efficient use of resources.
(Source): http://www.mnestudies.com/monitoring/what-monitoring

## Slide 5
Level in Objective Hierarchy | What to Monitor and Evaluate
Activities | Have planned activities been completed on time and within budget? What unplanned activities have been completed.
Outputs | What direct tangible products or services has the project delivered as a result of activities.
Outcomes | What changes have occurred as a result of the outputs and to what extent are these likely to contribute towards the project propose and desired impact.
Impact | To what extant has the project contributed towards its longer terms goals? Why or why not? What unanticipated positive or negative consequences did the project have? Why did they arise?
(Source): http://www.mnestudies.com/monitoring/what-monitoring

## Slide 6: Examples of Monitoring
M&E Focal points and/or M&E persons at CTI-CFF at Regional or National level are collecting regular data regarding health of coral reefs. They are feeding that into CT Atlas against output indicators set for health of coral reefs.
Regional Secretariat and country management are using that data to see if the project is making progress to improve health of coral reefs in CT6 region.

## Slide 7
Evaluation

## Slide 8: Definition of Evaluation
The word evaluation is taken from the French word ‘Evaluer’, that means merit/value or to draw out value (Barry, 1990)
An evaluation is a systematic and objective examination concerning the relevance, effectiveness, efficiency and impact of activities in the light of specified objectives/outcomes.
An important goal of evaluation is to provide recommendations and lessons to the project managers and implementation teams that have worked on the projects and for the ones that will implement and work on similar projects.
Source: https://en.wikipedia.org/wiki/Monitoring_and_evaluation

## Slide 9: Examples of Evaluation
CTI-CFF will (engage external consultant/s to) conduct evaluation of Regional Plan of Action “RPOA 2.0” at mid or end of plan.
CTI-CFF (External consultant/s) will collect evidences regarding impacts of projects and programs on biodiversity and marine life after certain time of projects/ programs implimentation.
Findings of evaluation will guide CTI-CFF at the National and regional levels to take decissions either to continue similar activities in case target areas are improved or to change key actions if target areas are not improved.

## Slide 10
INDICATORS

## Slide 11: Definition of Indicators
Indicator is a variable which indicates about any happening or phenomenon is called indicator (DFID, 2013). See Page 8 of this link:
  https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/304626/Indicators.pdf
  https://www.thecompassforsbc.org/how-to-guides/how-develop-indicators#main-content
Indicators are clues, signs or markers that measure one aspect of a program and show how close a program is to its desired path and outcomes. Indicators are realistic and measurable criteria of project progress. (M&E Studies, http://www.mnestudies.com/monitoring/what-indicators-and-types-indicators, accessed July 2020)
Indicators are something that can be measured objectively in qualitatively or quantitatively.
Indicators do not bear any specified value, these are variables and their value can vary from zero to hundred in percentage and/or number.

## Slide 12: SMART Criteria to Develop High-Quality Indicators
Specific: The indicator should accurately describe what is intended to be measured, and should not include multiple measurements in one indicator.
Measurable: Regardless of who uses the indicator, consistent results should be obtained and tracked under the same conditions.
Attainable: Collecting data for the indicator should be simple, straightforward, and cost-effective.
Relevant: The indicator should be closely connected with each respective input, output or outcome.
Time-bound: The indicator should include a specific time frame.
Source: http://www.mnestudies.com/monitoring/what-indicators-and-types-indicators

## Slide 13: Examples of Indicators
Indicators can be classified as follows:
1. Quantitative Indicators (Output Indicators)
Examples of Quantitative Indicators can be:
The number of people attending a training
The weight of fish caught
% of women involved in decision making while developing organization’s gender policy by the end of 2024.
2. Qualitative Indicators (Outcome / Performance Indicators)
Examples of Qualitiative or Perfomance Indicators are as follows:
Women’s participation in decision making
Participation in Youth Groups
Source: http://www.mnestudies.com/monitoring/what-indicators-and-types-indicators

## Slide 14
Targets

## Slide 15: Definition of Targets
Target is a quantified goal or objective that a programme plans to achieve by a certain date.
Targets should be set for all types of indicators in the logical flow from process to outputs, outcomes and impact.
Source: http://www.emro.who.int/child-health/research-and-evaluation/indicators/Targets-and-monitoring.html

## Slide 16: Examples of Targets
Under-five mortality will be reduced by two thirds between 1990 and 2015;
80% of under-five children with suspected pneumonia will be treated with antibiotics by (year);
70% of under-five children in malaria risk areas will sleep under insecticide-treated bednets by (year).
Source: http://www.emro.who.int/child-health/research-and-evaluation/indicators/Targets-and-monitoring.html
50% of women’s involvement in decision making while developing organization’s gender policy by the end of 2024.

## Slide 17
Milestones

## Slide 18: Definition of Milestones
Like targets, milestones also have a fixed value but their function is different as they have to show progress trajectory through project life
Source: https://www.merriam-webster.com/dictionary/milestone.
Hence, milestones are used as signal posts at different times of project life, for example, at start, at mid and at the end.

## Slide 19: Examples of Milestones
First milestone, 20% of women’s involvement in decision making while developing organization’s gender policy by the end of 2021.
Second milestone, 30% women’s involvement in decision making while developing organization’s gender policy by the end of 2022.

## Slide 20
Outcomes

## Slide 21: Definition of Outcomes
Outcome is the subject of result-based monitoring, it is specific and scientific statement regarding ultimate result of project activities, outputs and inputs on targets, populations or region, etc
Source: http://www.fao.org/3/a-au767e.pdf

## Slide 22: Example of Outcomes
In result of women’s involvement in decision making at policy level, women working for organization are feeling safe and empowered.

## Slide 23
OUTPUTS

## Slide 24: Definition of Outputs
Outputs are specific and scientific statements regarding immediate results of project activities and inputs on targets, populations or region, etc
Source: http://web.undp.org/evaluation/documents/HandBook/ME-Handbook.pdf

## Slide 25: Example of Outputs
Equal involvement of women in decision making at policy level is ensured in organization.

## Slide 26: Summary
At the end of this presentation and questions answers session. We expect that participants will learn about the basic definitions of key terms used in field of monitoring and evaluation.
This understanding of definitions of key terms used in field of monitoring and evaluation will help participants in setting monitoring and evaluation grounds for their respective projects and programs.

## Slide 27
Please ask your questions the floor is open.

## Slide 28
Thank you
Terima kasih Maraming salamat
Tank iu
Tagio tumas
Obrigado
Photos by Rumanti Wasturini & Ayodya Satryo Anggorodjati