## Slide 1
TECHNICAL WORKING GROUP
Mr Vagi Rei
SESSION 10.5: THREATENED SPECIES TECHNICAL WORKING GROUP
Chair of CTI-CFF THREATENED SPECIES WORKING GROUP

## Slide 2
Outlines
Focal Point
Partners
Status on TSWG Work Plan 2019
Decision endorsed in SOM 14 and its Status
Work Plan for 2020
Recommendation for SOM 15

## Slide 3
1. Focal Point
Country | Focal Point
Indonesia (Co-Chair) | Andi Rusandi, Director for Marine Conservation and Biodiversity, MMAF Supported by: Mr Firdaus Agung
Malaysia | Deputy General Director, Department of Fisheries Malaysia
Papua New Guinea (Chair) | Mr. Vagi Rei, Manager Conservation and Environment Protection Agency Supported by Phelameya Haiveta, Elton Kaitokai
Philippines | Asec Ricardo L. Calderon, Director of Biodiversity Management Bureau Supported Pablo delos Reyes, Jr and Ludivina L Labe
Solomon Islands | Ivory Akao, Ministry of Fisheries and Marine Resources Supported by: Agnetha Vave-Karamui, Chief Conservation Officer, MECDM
Timor-Leste | Pedro Pinto, Chief od Department of Conservation, Forestry and Fauna Ministry of Agriculture and Fisheries Supported by: Fernando da Silva, Senior Staff, Ministry of Agriculture and Fisheries
Notes: Malaysia: Alternate: waiting for Replacement of Mr. Ab. Rahim Gor Yaman (Retired)
Papua New Guinea: Elton Kaitokai
Philippines: Asec Ricardo L. Calderon, Director of Biodiversity Management Bureau
Solomon Islands: Same
Timor Leste: Junior Pascoal de Carvalho, Ministry of Agriculture and Fisheries

## Slide 4: 2. Partners
Role | Primary Partners
Technical Lead | The wildlife Conservation Society (WCS)
Coordination Support | Regional Secretariat
Technical Support | The Worldwide Fund for Nature (WWF), Conservation International (CI),The Nature Conservancy( TNC)

## Slide 5
3. Status on TSWG Work Plan 2019
Activities | Status
Identification training on sharks and rays | Completed
Hold the annual TSWG meeting back to back with the write-shop to finalize the M&E Indicators for TS/on the development of the Region-wide Assessment Report on Threatened /on the formulation of the Region-wide Conservation Plan for Marine Mammals, Sea Turtles and Sharks and Rays | Completed
Production of maps identifying the locations and migratory routes of the threatened species ( CT6 to submit to RS ) | Ongoing supported by WWF
Finalise the TOR of the TSWG | Completed

## Slide 6: 4. Decision Endorsed on SOM 14 and its Status
Threatened Species Working Group | Status
1.Note the progress of the TSWG to develop the Regional Conservation Plan of Threatened Species (sharks and rays, sea turtles and marine mammals); | Ongoing
2. Endorse TOR for pool of experts on threatened species as well as the list of pool of experts; | Done
3. Note and urge countries to move forward in formulating the assessment report on Threatened Species and also developing the national conservation plan for marine mammals, sea turtles, shark and rays | Ongoing
4. Note and urge countries to move forward in formulating the threatened species monitoring and evaluation indicators; | Ongoing
5. To recognize the need for Regional Secretariat and/or Partners to support and secure funding sources for the engagement of an experienced TSWG coordinator; | Done
6. Acknowledge the support of the German BMU through GIZ and CI to the TSWG in producing a draft outline of the regional conservation plan for sea turtles and other priority threatened species; and | Done
7. Endorse the work plan for TSWG for calendar year 2019 | Done
Notes: Those with Status ”ongoing” the TSWG has already include in their workplan in

## Slide 7: 5. Work Plan for TSWG 2020
Planned Activities | Venue | Time Frame | Proposed Budget | Source of Budget
Writeshop back to back on: M&E indicators Assessment report of Threatened species Regional Conservation Plan Prioritize list of Threatened species in CT Region Back to back with 4th Threatened Species Working Group Meeting | Manila, Philippines | Q1 (Jan – Mar) 4 days Meeting | Around USD40,000 (PHL, unable to commit but willing to host) | Regional Secretariat with Development Partners
Training for Trainers on Rapid Assessment Toolkit for Shark and Rays and MPA for Sharks (2 participants for each country) Include Note: WCS is able to provide the resource person as trainer. | TBC | Q1 (Jan-Mar) | USD30,000 | Regional Secretariat with Development Partners ( WWF and WSC)
Submission of Pool of Experts to IUCN SSC and engagement with the IUCN Red-list Team |  | Q1 (Jan – Mar) |  | No Budget Needed
Profile of Sharks and Rays in CTI Countries |  | Q1 (Jan – Mar) |  | No Budget Needed
Notes: Two major activities.

## Slide 8: 6. Recommendation for SOM 15th
Acknowledged that Indonesia has completed its conservation plan and country assessment report of threatened species (marine mammals, sea turtle, and sharks and rays) entitled “Assessment of Threatened Species in Indonesia” and it can be accessed on the CTI-CFF website. Encouraged other Member Countries to send their conservation plan and country assessment report by February 2020;
Acknowledged the submission of the CT6 Member Countries national conservation plan for marine mammals, sea turtles, sharks and rays to be compiled by the Regional Secretariat by February 29, 2020;
Endorsed the conduct of the Writeshop of the Regional Assessment of Threatened Species and national conservation plan for marine mammals, sea turtles, sharks and rays to be included in the TSWG Work plan for 2020;
Acknowledged and appreciated the contribution of WWF Indonesia on the development of Distribution Map of Threatened Species that will be completed by end of January 2020;
Endorsed the Terms of Reference of the Threatened Species Working Group;

## Slide 9: Recommendation for SOM 15th
6. Endorsed the Terms of Reference of the Pool of Experts;
Called on the Development Partners for continued support on the development of the Assessment of Threatened Species and National Conservation Plan of the CT6 Member Countries;
Endorsed the conduct of the Writeshop for the Finalization of M&E indicators in 1st Quarter of 2020; and
9. Endorsed the TSWG Work Plan for 2020.