## Slide 1
SOM14
14th Senior Officials’ Meeting
12 - 13 December 2018
Manila, Philippines
SESSION 8: TECHNICAL WG
Dr Nagulendran Kangayatkarasu
Chair of CTI-CFF CCA Working Group
Climate Change Adaptation (CCA) Working Group

## Slide 2: Outline
Focal Points & Partners
Status on Decisions Endorsed by SOM 13
Highlights of Accomplishments
Status of 2018 workplan
Challenges
Proposed Work Plan for 2019
Recommendations for SOM14 Consideration

## Slide 3: Focal Points
Member Country | Focal Point
Indonesia | Sri Tantri Arundhati, Ministry of Environment and Forestry Supported by Nuraieni
Malaysia (Chair) | Dr Nagulendran Kangayatkarasu Under Secretary of Strategic Technology Application Division, Ministry of Energy, Science, Technology, Environment and Climate Change (MESTECC) Supported by: Dr Ejria Salleh
Papua New Guinea | Kay Kumaras Kalim, Director, Conservation and Environment Protection Agency Supported by: Iki Peter
Philippines (Co-Chair) | Noel Antonio Gaerlan, Undersecretary, Climate Change Commission Supported by: Alexis Lapiz
Solomon Islands | Agnetha Vave-Karamui, Chief Conservation Officer, Ministry of Environment, Climate Change, Disaster Management and Meteorology Supported by: Nelly Kere
Timor-Leste | Rui dos Reis Pires, Ministry of Commerce, Industry and the Environment

## Slide 4: PARTNERS
ROLE | PRIMARY PARTNERS
Coordination and Support | CTI-RS
Technical Lead | WWF
Technical Support | Government of Australia, The Nature Conservancy (TNC), Conservation International (CI)

## Slide 5: CCA Accomplishment to date
2011: Joint Communique on Climate Change which was submitted during UNFCC COP19 in Denmark.
2012: Region-wide Early Action Plan (REAP) on CCA.
2013: Local Early Action Planning (LEAP) guide, identification of CCA regional priorities and development of adaptation marketplace.
2014: Statements on CC in World Parks Congress.
2015: Side event during UNFCC “Pathway to CC: Financing for Small Islands Developing States”.
2016: Regional Workshop on Center of Excellence (COE) establishment (National and Regional).
2017: Climate Change Impacts and Coastal Adaptation of Coastal Community within the South China Sea.
2018: 5th CTI-CFF Climate Change Adaptation Working Group Regional Exchange and Grant-Writing Workshop

## Slide 6: Status on Decisions Endorsed by SOM13
Decisions Endorsed by SOM 13 | Status
Noted the progress of the working group on the establishment of Center of Excellence on climate change adaptation at national and regional level and directed the WG to continue the discussions and pursue actions that will lead towards the attainment of Target 2 of Goal 4 of the RPOA; | Being implemented locally
Tasked the working group to develop further the draft Terms of Reference for the establishment of the CTI Center of Excellence on climate change adaptation; | Ongoing
Tasked the Regional Secretariat to allocate funds to implement the feasibility of the operation and maintenance of CT Atlas data according to SOM11 Decision; | Proposal on CT Atlas has been submitted to CTI RS by WorldFish, subject for approval of CSO
Enjoined the partners and collaborators to assist the CT6 in updating the CT Atlas for the Climate Change Adaptation Monitoring and Evaluation Indicators; | Proposal from CT Atlas has been submitted to CTI RS by WorldFish, subject for approval of CSO
Adopted the regional work plan on Blue Carbon Initiative for carbon storage as a means to maintain healthy marine and coastal ecosystem in the CT region; | Focus on 2019 - to do capacity building and based on capacity, urge other CT6 countries to implement their National Work Plan
Called on partners to assist Regional Secretariat in sourcing funds to support the various capacity building activities of the CCA WG; | Ongoing
Approved the CCA TWG Work Plan 2018. | Done
Notes: PH: Set up a localised a TWG and has implemented in Siargoes Islands – plan to set up in Camotes Island (Del Carmen has adopted the localised WG) as well as Sorsogon; in coordinationwith local
government
Indonesia: establish one Center of Excellence (Physical structure) for all aspects of CTI not only for climate change – (suggestion)
PH : to establish a center to serve as regional hub. However, to ensure that the impact is felt on the ground, agreed to localise the implementation
Chair: establish own localised center ad link it to RS and share information
Malaysia: Last april, virtual network is agreed to be established – progress is very slow; blue carbon is the focus – hope for more collaboration and network among CT6 (2) LEAP –
PNG: Have a central cooridnating agency; a university have established a research center
Chair: Things are happening at the country level
TL: has a COE in the university focus on biodiversity and climate change ---
(2)The draft of TOR

## Slide 7: Status of 2018 Work Plan
Planned Activities | Status
Grant-writing proposal workshop to be hosted by Malaysia | Completed
Capacity building activity on Blue Carbon to be hosted by Indonesia | Partially implemented – Timor Leste and Indonesia – with support from Australian Govt’ and CTC
Communication, Education and Public Awareness Training on Blue Carbon to be hosted by Solomon Islands | Capacity building on blue carbon and CEPA activity to be hosted by Indonesia, subject to support of donors/funding availability
Adopted the regional work plan on Blue Carbon Initiative for carbon storage as a means to maintain healthy marine and coastal ecosystem in the CT region; | Focus on 2019 - to do capacity building and based on capacity, urge other CT6 countries to implement their National Work Plan
Called on partners to assist Regional Secretariat in sourcing funds to support the various capacity building activities of the CCA WG; | Ongoing
Approved the CCA TWG Work Plan 2018. | Done
Notes: Blue carbon – 3rd annual meeting; CCA WG rep funded by Blue Carbon prtners
Chair: Capacity building o CEPA? Or do we need CEPA
Malaysia has no firm posiiton on blue carbon – what activities to drop
INDonesia: Has not happen fully but with the support of CTC – only in the Pilot (TL)

## Slide 8
Planned Activities | Status
Conduct 6th CCA TWG meeting back to back with CT Atlas training | Training on CT Atlas to be conducted in 2019 (subject to budget approval)
Development of the Executive Course on CCA | Ongoing (reviewing course outline)
Development of TOR of CTI on COE of CCA | Done - Level 1 and 2
Notes: Regional exchange to reflect and prioritise on what the CCA WG want to be included in the RPOA Revision.
-

## Slide 9: Proposed Work Plan/Activities for 2019
Activities | Time Frame | Budget (including Budget Source)
Blue Carbon Capacity Building Workshop to be hosted by Indonesia subject to funding availability | Q2 | Subject to funding availability
CCA TWG Meeting (PH to host- tentative) finalization of CCA Executive Course familiarize and update M&E Indicators Update on Blue Carbon Capacity Building Workshop Update on Center of Excellence (COE) | Q2 - Q3 | Regional Secretariat
CT Atlas Inception Workshop taking into account input from CCA (subject to budget approval) | Q1 (tentative) | Regional Secretariat
Update the REAP through open participatory of CT6 countries. (Note: The Review of the RPOA will have elements of LEAP and REAP) | Q2 | Regional Secretariat
Notes: Important to Note that each TWG has to priorities what activity they would like to see happening in 2019. Please note that RS has only $24000 USD per activity in 2019 budgeted for and only one 1 NCC per country can visit

## Slide 10: Recommendations for SOM14 Consideration
Appreciate the support provided by Development Partners to the CCA WG;
Reprioritize, revisit and refocus issues affecting CT6 member countries, particularly on CCA what to do in subsequent years for inclusion in the RPOA revision;
Note that a draft has been developed on the Executive Course of CCA – Introductory levels 1 and 2 - and urge other CT6 member countries to give comments by 30th March 2019; Task the CTI Regional Secretariat to recirculate the draft to CT6 member countries;
Agree to carry over the implementation of two activities - the capacity building on Blue Carbon and CEPA activity in 2019 subject to availability of funds and acknowledge Indonesia to host the activities;
Note that after completing the two activities (mentioned in Item 3), CT6 are encourage to come up with their respective Blue Carbon roadmap/initiatives subject to national circumstances;
Agree for virtual regional Center of Excellence (COE) hosted by the existing CTI website with inputs from respective national COEs through their respective NCCs;
Support the recommendation of the CCA WG to turnover the Chairmanship from Malaysia to Philippines and the turn-over of the Co-Chairmanship from PH to PNG based on the provisions stipulated in the Rules of Procedure of the CCA WG; and
Approve the CCA TWG Work Plan 2019.

## Slide 11
Terima Kasih - Maraming Salamat Tank Iu- Obrigado Tagio Tumas
Photo credits: IYORBank_Rebecca Weeks and Yen-Yi Lee