## Sheet1
LOGICAL FRAMEWORK ANALYSIS (LFA) 2010 - 2020
CTI - CFF
REGIONAL PLAN OF ACTIONS
GOALS | TARGET (Outcomes) | MEASURABLE INDICATORS (Deliverables) | REGIONAL ACTION (Outputs) | ACTIVITIES (Past and Planned - Regional level) | REPORT *status
1. Priority SEASCAPES | Priority Seascape Designated, with Investment Plans Completed and Sequenced | Number of priority seascapes designated with investment plans | 1. Through regional collaboration, conduct Rapid Seascape Assessments for the entire region, in order to delineate seascapes and identify priority seascapes for investment | - Engage technical experts / consultants to collate and synthesize data/information - The TWG to share information with NCCs and what information would be useful to collect - Technical experts / consultants share collated information with NCCs - Present preliminary results at 1st Seascapes Regional Exchange | Not started
| Marine and Coastal Resources within All Priority Seascapes are being Sustainably Managed | Number of priority seascapes under continuous improved management | 1. Adopt a general “model” for the sustainable management of seascapes | - Intercessional sub-committee appointed to draft a general model - Presentation of draft model at Seascape WG - Presentation of general model to SOM for endorsement | Sulu-Sulawesi Marine Ecoregion (SSME) ; Bismarck Solomon Seas Ecoregion (BSSE)
|  | Regular regional meetings to strengthen and synergise management of priority seascapes | 2. Establish seascape capacity-building and learning mechanism | - 1st Seascape Regional Exchange for building understanding of seascape management - 2nd Seascape Regional Exchange for CB (incld development for investment plan) | Completed
|  | Coordinating body for each “priority seascape” established to guide, monitor and track efforts in the seascape | 3. Through joint and single-country efforts, start to mobilize the financial resources necessary to support “priority seascape” programs (based on Seascape Investment Plans). | - Secure government funding allocation by …. - Develop private sector support through …. - Develop private donor support through …. | Mobilize the financial resources necessary, including new and additional funding, to support designated priority Seascape programs across the region from both domestic and international funding sources.
|  | Monev report shows status of priority seascape management, whether its improved, stagnant or decreased | 4. Conduct periodic monitoring and evaluation of priority seascape programs - Monev Indicators for Seascape available | Develop and agreed upon monev indicators for Seascape Periodic Monitoring and evaluation of priority seascape programs | Not started
2. EAFM | Strong legislative, policy and regulatory frameworks in place for achieving an ecosystem approach to fisheries management (EAFM) | Number of policies and regulations promoting EAFM at regional and national levels with regulatory framework and budget allocated for their operationalization | 1. Collaborate to develop a “common regional framework for legislation and policy” that would support EAFM; drawing on this, strengthen regional and national legislation, policies, and regulations (2012) | - Convene a technical workshop on scientific guidance to incorporate climate change and ocean acidification into EAFM network - Under the Sulu-Sulawesi Marine Ecoregion involving Indonesia, Malaysia and Philippines (SSME) and the Bismarck-Solomon Seas Eco-region involving PNG and the Solomon Islands (BSSE) arrangement, conduct a project to develop and incorporate EAFM in fisheris management - Incorporate learning into all existing fisheries management plans - EAFM knowledge exchange and training on fisheries prioritization exercise - Ministerial/agency capital building to each CT6 - Provide guidance to assist in developing national policies on climate change and ocean acidification into EAFM - Conduct national EAFM prioritization exercise - Conduct one pilot study per country to develop fishery-specific management plan that incorporates EAFM | Not started; Initiated for Sulu-Celebes sea Ibid above On going Initiated (EAFM LEAD) Not started Ongoing Ongoing
|  | Number of joint enforcement programme among CT6 countries with national to global agencies Number of arrest and or legal process for IUU fishing increased System for documentation/database/information sharing | 2. Improve enforcement of IUU fishing through greater collaboration | -Establish regional forum the address IUU fishing / engagement with RPOA IUU in South China Sea and Sulawesi - Collaboratively address trans-boundary MCS (SEA and South Pacific) - Convene MCS practitioner workshop (REX) to share info and knowledge exchange - Continue IUU cooperative work in North Sabah, Palawan on LRFF enforcement - Implement VMS (vessel monitoring system) for monitoring fishing activities of large-scale and transboundary fishing fleets | Completed Ongoing Ongoing Not started
|  | Number of CTI-CFF commitments and agreements (eg. projects and programs) that have incorporated PES | 3. Incorporate EAFM and payments for environmental services (PES) in bilateral and regional commitments on fisheries management (on-going) | - CT6 Regional workshops on PES - CT6 and Development Partners Consultative Meeting on Adoption of PES in Government's commitment and agreements
| Improved income, livelihoods and food security in an increasingly significant number of coastal communities across the region through a new sustainable Coastal Fisheries and Poverty Reduction Initative (COASTFISH) | Each CT6 countries have quantitative targets for COASTFISH - should look on SDGs per country as reference CTI have regional quantitative targets for COASTFISH % of communities targeted have improved income, livelihood and food security | 1. Design and launch a region-wide CTI-COASTFISH initiative EAFM TWG Action: Poverty Reduction through sustainable management of coastal fisheries | - Draw up guidelines for implementation of EAFM for coastal fisheries - Application of appropriate technical materials on coastal fisheries management at a community-based level on fisheries management - Conduct value addition training for post-harvest coastal fisheries - Conduct feasibility studies on by-catch and discards - Conduct value chain analysis on coastal fisheries - Produce map denoting locations of COASTFISH Sites or Regions - COASTFISH Investment Plan at a Regional Level | Not started
|  | Number of COASTFISH sites per country are based on poverty and biodiversity criteria Number of COASTFISH sites per country receive investment / funding | 2. Collaborate around the mobilization of significant new financial investments to support COASTFISH | - Develop proposals and seek for supports from private sectors and development partners, as well as providing co-financing mechanism in implementing COASTFISH Investment Plan above -> ie Regional Coastfish Fund - Conduct Investor Forums / meetings - Develop and share information on small-scale funding mechanism for fishers | Mobilize the financial resources necessary, including new and additional funding, to support EAFM programs across the region from both domestic and international funding sources
|  | Number of joint marketing deals (agreements) on a multi-country / regional level in a COASTFISH pilot projects CTI-CFF have realtime information system accessible to CT6 countries that brings about, for example: - Fishing ground - Migration flow | 3. Collaborate around technology and information sharing, lessons learned, and joint marketing of common products | - Technical supports for COASTFISH (scientific institutions, NGOs, private sector actors, or others) that are interested in multi country / regional level - Develop a system / mechanism of information, approach and technology sharing between CT6 countries - Develop a joint marketing mechanism between CT6 countries of common products in a collaborative system / agreements - Others ...??
| Effective measures in place to help ensure exploitation of shared tuna stocks is sustainable, with tuna spawning areas and juvenile growth stages adequately protected | Number of policies and agreements among the CT6 countries for the management of tuna | 1. Develop a collaborative work program on this topic that covers a wide range of activities, such as jointly supported research, information-sharing, strategies for protection of spawning and juvenile growth areas, and financing mechanisms (2010) | - Support regional tuna research (juvenile, nursery grounds) - Introduce and familirize PES, especially on tuna - Build capacity for tuna stock assessment | The first two were initiated by WWF; last one was initiated (no further info)
|  | Change in conservation status of tuna | 2. Establish an informal CTI Forum on Tuna Governance (2010) | - Hold a regional CTI Workshop / Forum on the Sustainable Management of Tuna in CT Region; purpose: increased influence on RFMOs from CT6 - Roadmap on Tuna Forum finalised in next EAFM meeting (coming August 3rd) | Not conducted yet, concept and TOR ready (developed)
| A more effective management and more sustainable trade in live-reef fish and reef-based ornamentals achieved | Number of policy/legislation adopted on live reef fish trade to decrease level of destructive fishing practices linked to the trade | 1. Develop a collaborative work program on management of and international trade in coral-reef-based fish and ornamentals (2010) | - Regional coordination of MPAs eg CTMPAS Framework - Regional standard developed, applied and monitored, regional database maintained., accrediation recorded - Regional coordination to prevent / reduce trans-boundary IUU Fishing and Illegal Trading practices (RPOA IUU currently does not cover LRFFT) | First and third activities not conducted Second activity: WWF and ASC commenced work on grouper and barramundi standard development
|  | Number and area (sq km) of locally managed areas for live reef fish trade | 2. Establish an informal CTI Forum on management of and international trade in coral-reef-based organisms (2010) | Forum to devep standards, support development of national database and maintain regional database | Not started
3. MPAs | Region-wide Coral Triangle MPA System (CTMPAS) in place and fully functional | CTMPAS Framework developed and adopted by CT6 | 1. Jointly establish overall goals, objectives, principles, and operational design elements for a CTMPAS centered around priority MPA networks (2010) | - Share result of first round nomination with the CTMPAS Review committee - Submissions of nombination for country flagship and priority development sites (Categories 3 and 4) for inclusion in CTMPAS (second round) - Appoint the MPA Coordinator to guide CTMPAS implementation and provide overall support to MPA TWG - Conduct periodic CTI MPA-TWG meetings and MPA Advisory Group meetings - Review and refine CTMPAS nominations (2nd round) - Review by external independent CTMPAS review committee - Mobilize partners and other donor projects to support (including funding) for CTMPAS implementation during CTI and other international workshops - Provide recognition awards of CTMPAS sites and progress every two years starting 2016 to coincide with the CT Day and/or other CTI related celebration | Copy of CTMPAS Framework; Minutes of CTI MPA-TWG meeting; SOM decision document endorsing CTMPAS for implementation
|  | Percent/area of total marine habitat area in CT region in marine protected or managed areas | 2. Complete and endorse a comprehensive map of MPA networks to be included in CTMPAS (2012) | - Determin CT Atlas vocal points per country - Input all national MPA data (recognised category 1 site) into CT Atlas for tracking national and regional progress - CT Atlas annual report on the country MPA status to the NCCs and MPA TWG - MPA M&E Indicators are tracked with data inputs/updates from countries to track progress and change - Request for technical assistance to each country to improve national MPA data quality and consistency for CT Atlas tracking following CT Atlas protocols - CT Atlas institutional base is supported and expanded to perform data management, analysis and reporting function | CT Atlas map; CTMPAS progress report; Area of MPAs by country and in region; Trend map showing change over time in percentage/area of total marine habitat area in CT region inside MPAs
|  | Percent/area of each major marine and coastal habitat type in strictly protected “no-take replenishment zones” | 3. Build capacity for effective management of the CTMPAS (on-going)
|  | Percent/Area (in hectares) of marine protected areas under “effective” management | 4. Collaborate around mobilizing sustainable financing for the CTMPAS (on-going) |  | MPA management effectiveness assessment ratings/Report for each MPA recorded in CT Atlas; CT Atlas map and percent of MPAs with level of effectiveness meeting CTMPAS Category 2 criteria.
5. Establish MPA networks, particularly those involving more than one country (on-going)
|  | Percent/Area of marine protected/ managed areas included in CTMPAS | 6. Establish a public/private partnership (PPP) or working group for engaging relevant industries in supporting CTMPAS
4. CCA | Region-Wide Early Action Plan for CCA for the near-shore marine and coastal environment and small island ecosystems developed and implemented | Number of regional agreements/frameworks/ plans (e.g. region-wide early action plan (REAP) developed | 1. Identify the most important and immediate adaptation measures that should be taken across all CT countries, based primarily on analyses using existing models (2011) |  | The development of the Region-wide Early Action Plan for Climate Change Adaptation for the Nearshore Marine and Coastal Environment (REAP-CCA).
|  | Number of national policies (including national CCA plans and frameworks), laws and regulations on climate change adaptation proposed and adopted | 2. Identify the most important and immediate adaptation measures that could be taken in each CT country (2011)
|  | Percentage of local governments that have integrated climate adaptation into local governance (plans and actions) | 3. Complete and implement a Region-wide Early Action Plan for CCA (plan:2012; full implementation: 2015) | - Compile and review existing guidelines and baseline assessment and (—rehabilitation methodologies - Develop damage assessment and valuation monitoring guidelines | The REAP-CCA was developed and adopted in 2011 as part of regional action 3 under Target #1.
|  |  |  | - Develop draft and final regional guidelines - Assess feasibility of establishing a CT Rehabilitation Fund [CTI-PPF - (as part of CTI development fund) check with FRWG] | Draft CCA Guide had been developed and piloted to support local implementation of the REAP-CCA (Regional Action 3, Target #1).
|  | Area of mangrove (REAP 1&2) | 4. Conduct capacity needs assessment and develop capacity building programs on CCA measures (2011) | - Conduct annual regional training course on CCA vulnerability and assessment and planning based on LEAP Guide and other methodologies and tools - Conduct a Regional CCA F orum to share vulnerability assessment h methodologies and results of CCA programs - Acquire Global Mangrove Information System (GLOMIS) - data from International Society for Mangrove Ecosystems - Establish and maintain a CCA Virtual Forum for knowledge management on CCA learning, tools, products, and case studies developed in the Coral Triangle as part of CTI website with links to national CT country at centers and other CCA knowledge portals | Capacity building program have been conducted at the sub-regional level participated by a total of 61 participants (24 for the batch attended Solomon Islands and PNG; 30 for the batch attended by Malaysia and the Philippines and 27 for the batch attended by Indonesia and Timor Leste.
|  |  | 5. Mobilize financial resources to implement REAP for Climate Change Adaptation | - Conduct regional training/workshop for CTE on developing proposals for funding CCA Projects - Post CCA project proposals on the CCA Marketplace - Identify other funding sources for CCA projects Ongoing - Conduct meeting with other Goals to evaluate funding status | Ongoing
| Networked National Centers of Excellence on CCA for marine and coastal environments are established and in full operation | A national institution within CT6 designated and networked to address climate change adaptation coordinated with national government support | 1. Collaborate around the design and implementation of a Pilot Phase for National Centers of Excellence (Design of Pilot Phase: 2012; Full Implementation: 2014) | - Conduct regional workshop to proposed /existing national institutions to share and define criteria/benchmarks/TOR for COP Develop common set of guidelines for strengthening COE and a regional networking action plan - Identify and establish a COE at national level in each country based on the guidelines - Develop regional/national incentives for achieving COE standards - Conduct a workshop of regional network of COE to develop a 5-year plan to compile and publish climate science and adaptation case studies as input to the next IPCC report - Conduct annual workshop to share climate science and adaptation case studies and monitor progress against the 5-year plan | Target #2: Networked national centers of excellence on climate change adaptation for marine and coastal environments are established and in full operation. Attempts to involve national universities during the subregional training i.e. University of PNG, Solomon Islands College of Higher Education, University of Malaysia and the University of the Philippines-Marine Science Institute. Varying degree of information exchanges (at the individual) were occurring to a limited extent.
5. Threatened Species | Improved status of sharks, sea turtles, seabirds, marine mammals, corals, seagrass, mangroves and other identified threatened species | Number of new policies or agreements adopted at the regional and national levels that are in compliance with the international agreements on threatened species | 1. Assess species status by supporting ongoing and new assessment programs (2012) | Undertake baseline assessments of existing initiatives on the conservation and management of sharks, marine turtles, seabirds, marine mammals, corals, seagrass, mangroves | Ongoing
|  | Area (in hectares) of protected marine habitat that contributes to conservation of for threatened and endangered species protected | 2. Complete and implement region-wide threatened species conservation and management action plans (sea turtles, marine mammals, sea birds, sharks) | - Conduct regional exchanges to complete the Conservation Action Plans for Sharks, Marine Turtles, Mammals, and seabirds - Expand implementation of the SSME Comprehensive Action Plan for Charismatic, Threatened and Migratory species to the CTI - Initiate sustainable financing and partnership-building for the implementation of the above-mentioned action plans | Ongoing
Number of threatened species with improved status (to be decided by CTI as a body or by a forum designated by the CT6 according to IUCNred list criteria assessment or other criteria to be determined by CTI)