## Slide 1
SEASCAPE
TECHNICAL WORKING GROUP
Ms. Yvonne Tio
Chair of Seascape TWG

## Slide 2
Outline
Focal Points
Action Taken for SOM-16 Decisions
CTI-CFF/UQ/GEF proposed project
Update on Workplan and Budget by the Chair of SWG for 2022
Workplan and proposed Budget by the Chair of SWG for 2023
Draft Recommendations for SOM 17

## Slide 3
Focal Points
Member Country | Focal Points
Indonesia | Focal Point: Mr. Suharyanto, M.Sc , Director of Marine Spatial Planning, Directorate General Marine Spatial management, Ministry of Marine Affairs and Fisheries. Alternate: Mr. Rusman Manafi , Assistant Deputy for Coastal and Marine Spatial Management, Coordinating Ministry for Maritime Affairs and Investment
Malaysia | Focal Point: Dr Norasma Dacho, Principal Assistant Director for Resource Management and Conservation Office, DOF Sabah Alternate: Ms. Sylvia Scholastica Michael Dalansing , Fisheries Officer, Department of Fisheries Sabah
Papua New Guinea (Chair) | Focal Point: Ms. Yvonne Tio, Executive Manageress, CEPA Alternate: Ms Phelameya Haiveta. CEPA
Philippines | Focal Point: Ms. Natividad Y. Bernardino, OIC Director, Biodiversity Management Bureau, DENR Alternate: Atty. Demosthenes R. Escoto, OIC Director, Bureau Fisheries and Aquatic Resources Support Staff: Ms. Janice Tuante Cubo , Aquaculturist II, BFAR and John Erick Avelino, OIC Section Chief, Biodiversity Management Bureau DENR
Solomon Islands | Focal Point: Ms. Assaneth Buarafi, Chief Fisheries Officer, Inshore Fisheries Management, Ministry of Fisheries and Marine Resources Alternate: Mr. Trevor Maeda, Ministry of Environment Climate Change Disaster Management and Meteorology and Mr Brian Akwasia , Ocean and Climate Desk Officer, Ministry of Foreign Affairs and External
Timor-Leste (Co-chair) | Focal Point name : Mr. Fidelino Sousa Marques, Chief Cabinet of General Directorate of Fisheries, Aquaculture and Marine Resources. Alternate name : Mr. Delio da Costa Technical Staff for Department of R&D for Fisheries and Aquaculture. Support Staff: Dominica Paula Jerónimo Guterres, Technical Staff at Department of Marine Spacial Plan and Marine Aquatic Management

## Slide 4: Action taken for SOM-16 Decisions
Decisions | Status
Acknowledged and appreciated the presentation by Seascape Working Group (Annex 30) | Done
Agreed the Sub-Regional Working Groups for Priority Seascape (Annex 31), Sulu-Sulawesi Priority Seascape Sub-Regional Working Group Terms of Reference (Annex 32), Terms of References for Lesser Sunda Priority Seascape Sub-Regional Working Group (Annex 33) and Bismarck Solomon Sea Ecoregion Priority Seascape Sub-Regional Working Group (Annex 34) | Done
Acknowledged and appreciated the support of USAID Oceans and Fisheries Partnership to the Regional Planning and Consultative Workshop for Priority Seascapes (In conjunction with the EAFM SSS Planning and the Regional Strategic Action Plan) | Done
Acknowledged and appreciated the update on SOMACORE project by the Seascape Working Group (Annex 35 a b), and requested GIZ to officially update and discuss with each CT 6 NCCs and SWG particularly on the Steering structure and management of the project once it is approved | Commissioned by the German Federal Ministry in July 2022
Acknowledged and appreciated the update on the proposal of University of Queensland, CI Philippines and UNDP on the Seascape Approach to Securing Coral Reef Fishery and Biodiversity Resources in the Sulu Sulawesi Seascape Strategic Action Plan | In process

## Slide 5: Action taken for SOM-16 Decisions
Decisions | Status
Agreed to endorse the Strategic Action Plan (SAP) on Seascape Approach to Securing Coral Reef Fishery and Biodiversity Resources in the Sulu Sulawesi Seascape (Annex 36) | Done
Urged the NCCs ( ID, MY) to procure the Federal/National Ministerial level signatures for the SAP on Seascape Approach to Securing Coral Reef Fishery and Biodiversity Resources in the Sulu Sulawesi Seascape (Annex 37 as well as the GEF Country Nodes signatures for the PIF to the SAP on Seascape Approach to Securing Coral Reef Fishery and Biodiversity Resources in the Sulu Sulawesi Seascape (Annex 38) | Sent a reminder to the member countries on 10 March 2022 following our letter NCC.RS.9.21.365 Indonesia already provided the signature and authorization letter Malaysia already provided the signature and yet to submit the authorization letter Philippines already provide the name but, yet to provide the signature
Acknowledged and appreciated the support of USAID RDMA through the Sustainable Fish Asia SuFIA project and programs related to Seascape | On going

## Slide 6: Action taken for SOM-16 Decisions
Decisions | Status
Acknowledged the current situation caused by the Covid 19 Global Pandemic which affects the Seascape Working Group to implement the Work Plan of 2020 | Done
Noted the postponement of the 7th Seascape Working Group Meeting back-to-back with Seascape Working Group Regional Exchange to be undertaken in 2022 | Defer to 2023
Approved the Seascape Working Group 2022 Workplan (Annex 39) | Done
Supported the recommendations of the Seascapes Working Group to turn over the Chair from Malaysia to Papua New Guinea and the turnover of the Co Chair from Solomon Islands to Timor Leste, based on the provisions stipulated in the Rules of Procedure of the CTI CFF Seascapes Working Group (Annex 40) | Done
Acknowledged and appreciated the excellent chairship of Dr Norasma Dacho from Malaysia as Chair and Ms Agnetha Vave Karamui from Solomon Islands as Co Chair of the Seascapes Working Group for the period of 2018-2020 | Done

## Slide 7
RS circulated to all the NCCS of southeast Asia Countries
Reference letter: NCC.RS.9.21.365-New Revised New Revised SAP and Endorsement Documents, and Request for Federal Ministers’ Names for Signatures [Sent on 10 September 2021].
RS circulated to all the NCCS of southeast Asia Countries and the Drafting committee
Reference letter: TWG.RS.10.21.480_Circulation of the full draft Projection Identification Form (PIF) of the CTI-CFF Sulu-Sulawesi Seascape GEF proposal [Sent on 19 October 2021].
We sent a reminder to the member countries on 10 March 2022 following our letter NCC.RS.9.21.365 on New Revised SAP and Endorsement Documents and Request for Federal Ministers’ Names for Signatures. Since then, no countries have responded to our reminder.
Recently RS sent another letter on SAP and Endorsement Documents, and Request for Federal Ministers’ Names and Signatures for GEF-8 Submission (NCC/RS/6/22/132 dated 9 June 2022).
Based on the discussion during Seascape WG meeting on 31 October 2022 RS sent a reminder (same email thread of NCC/RS/6/22/132 on 7 November 2022) to Malaysia and Philippines NCCs Requesting for Federal Ministers’ Names and Signatures for GEF-8 Submission
CTI-CFF/UQ/GEF proposed project

## Slide 8: Federal Ministers’ Names for Signatures
Indonesia
Name: Victor Gustaaf Manoppo on behalf of Minister
Designation: Director General of Marine Spatial Management
Ministry: Marine Affairs and Fisheries, Indonesia
Signature:
Malaysia
Name: Jamalulail Bin Abu Bakar on behalf of Secretary General
Designation: Under Secretary Environmental Management Division
Ministry: Ministry of Environment and Water, Malaysia
Signature:
Philippines
Name: Honorable Maria Antonia Yulo Loyzaga
Designation: Secretary
Ministry: Department of Environment and Natural Resources.
Signature: __________________

## Slide 9: Update on Workplan and Budget for 2022
Planned Activities | Time Frame | Budget (USD) | Status
7th Seascape Working Group Meeting TOR (LSS) back-to-back with Seascape Working Group Regional Exchange for CT6 Activities defer to 2023 | Q2 | USD 5,280 | SWG In-Situ online meeting was conducted on 31 October 2022 back-to-back with EAFM
CT3 Southeast Asia NCCs procurement of Ministerial level signatures |  |  | Waiting for the signature and supporting documents from MY and PH
Infographics on Priority Seascapes by GIZ through SOMACORE |  | by GIZ through SOMACORE | Defer to 2023 (GIZ to support)
Output B1.1.I.a Output: By 2023 an updated assessment of resources, needs and opportunities of sustainable livelihoods and enterprises in targeted coastal areas including Priority Seascapes is conducted and completed, based on 2020 baseline information Output Indicator B1.1.I.a An assessment of resources, needs and opportunities of sustainable livelihoods and enterprises in targeted coastal areas including Priority Seascapes is conducted and completed, by 2023 # of Capacity Assessment Reports prepared by 2023 |  | Depending on funding | The Program Agenda for the workshop on “Assessment of Resources, Needs and Opportunities for Sustainable Livelihoods and Enterprises in Coastal Areas” Shared with CTI-CFF and SWG along with the meeting notes from last SWG online meeting (20 April 2022). This event was cancelled as there was no response for confirmation from the SWG members within the deadline given.

## Slide 10: Workplan and Propose Budget for 2023
Planned Activities | Time Frame | Budget (USD)
7th Seascape Working Group Meeting TOR (LSS) together with Seascape Working Group Regional Exchange for CT6 | Q1 – Q2 | USD 8,500
CT3 Southeast Asia NCCs procurement of Ministerial level signatures | Q1? (Before March) | Waiting for the signature and supporting documents from MY and PH
Infographics on Priority Seascapes by GIZ through SOMACORE | Q1-Q2 | Supported by GIZ
Workshop Output B1.1.I.a Output: By 2023 an updated assessment of resources, needs and opportunities of sustainable livelihoods and enterprises in targeted coastal areas including Priority Seascapes is conducted and completed, based on 2020 baseline information Output Indicator B1.1.I.a An assessment of resources, needs and opportunities of sustainable livelihoods and enterprises in targeted coastal areas including Priority Seascapes is conducted and completed, by 2023 # of Capacity Assessment Reports prepared by 2023 | Q1-Q2 | Subject to further discussion between RS and SuFiA TS/USAID RDMA

## Slide 11: Recommendations for SOM 17
Acknowledged and appreciated the presentation by Seascape Working Group (Annex 1);
Acknowledged and appreciated the support of USAID RDMA through the Sustainable Fish Asia (SuFia) project and programs related to Seascapes;
Acknowledged and appreciated the SOMACORE Project which was already approved by the German government;
Agreed on the conduct of the 7th Seascape Working Group Meeting together with Seascapes Working Group Regional Exchange to be undertaken in 2023 through In-situ online. Provided there is external funding support, a physical meeting might be held;
Appreciated and acknowledged Indonesia, Malaysia, and Philippines to provide the signature of the secretary/ministers from the concerned department and authorization letter for GEF 8 submission (Annex 2);
Acknowledged and appreciated the effort from Professor Peter Mumby of the University of Queensland and his work together with CI Philippines on the Seascape Approach to Securing Coral Reef Fishery and Biodiversity Resources in the Sulu-Sulawesi Seascape Strategic Action Plan;
Approved the Seascapes Working Group 2023 Workplan;