## Slide 1
THREATENED SPECIES
TECHNICAL WORKING GROUP
Mr. Firdaus Agung
Chair of TS TWG

## Slide 2
Outline
Focal Points
Action taken for SOM-16 Decisions
Update on Workplan and Budget by the Chair of TSWG for 2022
Workplan and proposed Budget by the Chair of TSWG for 2023
Draft Recommendations for SOM 17

## Slide 3
Focal Points
Member Country | Focal Points
Indonesia (Chair) | Mr. Firdaus Agung, Director for Marine Conservation and Biodiversity, MMAF; Supported by: Ms. Yudit Tia Lestari, Marine and Coastal Ecosystem Manager, MMAF
Malaysia | Mr. Bohari Haji Leng, Senior Director of Fisheries Conservation and Protection Supported by Mr Azlan Md Noor, Head of Conservation, Ecosystem and Biodiversity
Papua New Guinea | Mr. Vagi Rei, Manager Conservation and Environment Protection Authority. Supported by Ms. Phelameya Haiveta, Program Officer Marine Division, Sustainable Environment Programs. Conservation and Environment Protection Authority
Philippines (Co-Chair) | Atty. Demosthenes R. Escoto, OIC Director, Bureau of Fisheries and Aquatic Resources (BFAR), Department of Agriculture
Solomon Islands | Paul Tua, Chief Fisheries Officer, Inshore Fisheries Division, Ministry of Fisheries and Marine Resources. Alternates: Mr. David Aram, Principal Fisheries Officer, Inshore Fisheries Division, Ministry of Fisheries and Marine Resources; and Ms. Rose Babaua, Chief Conservation Officer, Ministry of Environment, Climate Change, Disaster Management and Meteorology
Timor-Leste | Mr. Benvindo Maria de Deus Araujo dos Santos (Junior Technical Staff under the Department of Conservation, Marine Biodiversity and Management of the Aquatic Enviroment). Alternate : Mr. Fernando da Silva (Senior Technical Staff under the Department of Conservation, Marine Biodiversity and Management of the Aquatic Enviroment).

## Slide 4: Action Taken for SOM 16 Decisions
Decisions | Status
1. Acknowledged and accepted the report of the Threatened Species Working Group (Annex 53); | Done
2. Encouraged the CT6 Member Countries to complete their National Assessment Report and Conservation Plan for Threatened Species by April 2022, to enable the Regional Assessment Report and Regional Conservation Plan to be compiled by the Regional Secretariat | Based on the meeting on 9 September 2022, countries are encouraged to focus and finish the National Assessment Report of Sharks and Rays
3. Acknowledged and appreciated the support of World-Wide Fund for Nature (WWF) in finalizing the Distribution Map of Threatened Species from CT6 Member Countries for CT Atlas, which has been uploaded by Regional Secretariat on the CT Atlas and for conducting the Training for Trainers on Rapid Assessment Toolkit (RAT) for Shark and Rays and MPA for Sharks in April 2021 | Done
4. Acknowledged and appreciated the finalized List of Threatened Species Pool of Experts on the draft webpage of CTI List of Experts | Done link: http://ctexperts.coraltriangleinitiative.org/
5. Appreciated the Regional Secretariat’s efforts to coordinate with IUCN SSC for submission of the Threatened Species List of Pool of Expert and encouraged the Threatened Species Experts to individually apply/register at this IUCN SSC link: https://bit.ly/35ghuzX | Done Link not valid

## Slide 5: Action Taken for SOM 16 Decisions (Con.)
Decisions | Status
6. Acknowledged the opportunity under the TRIPOD Project (Annex 56) for three of the CT6 Member Countries (Indonesia, Malaysia and Philippines ), and tasked the Regional Secretariat to work with WWF and TRIPOD Partners’ to explore CTI-CFF’s participation in Project TRIPOD for the remaining CT countries (Papua New Guinea, Solomon Islands and Timor-Leste) | Done
7. Appreciated the excellent contribution of Mr Vagi Rei as Chair from Papua New Guinea and Co-Chair Mr Andi Rusandi of Indonesia for the period of 2018-2021 | Done
8. Approved the TSWG 2022 Workplan | Done

## Slide 6: Update on Workplan and Budget for 2022
Planned Activities | Time Frame | Budget (USD) | Remarks
Write-shops: • National Assessment Report of Threatened Species • Regional Conservation Plan • Prioritized list of Threatened species in CT Region | April 2022 (Assessment Report of TS) | Virtual meeting USD 5,280 | TSWG In-Situ online meeting was conducted on 10 Nov. https://drive.google.com/drive/u/1/folders/15tS5KOUnijtjUVgAH6I26WS2Q6KBlbvZ Based on the discussion on 9 September meeting, CT6 to focus on Shark and Ray first and looking forward for the support from TRIPOD and SARRI Projects
Targeting Regional Investigations for Policing Opportunities & Development (Tripod) Project (MY, ID, PH): Governments to participate in national Counter-Transnational Organized Crime (CTOC) training Governments to seek involvement in the national taskforce NCCs participate in CTOC instructor course and regional workshops NCCs seek involvement in the regional taskforce | Jan-Mar 2022 *Specific dates to be confirmed Jun-Oct 2022 *Specific dates to be confirmed | Funded by TRIPOD partners if elected (noting Leahy Vetting is required) | The CTOC and CCW training are completed include the ShellBank (Marine turtle traceability) in ID and MY. ID: organized by Indonesia National Police (INP), MMAF and WWF-ID, Representatives from 25 law enforcement agencies nationally include NCC, BRIN, academics, etc. (August – Sep 2022) MY: Organized by Sabah Wildlife Department and WWF-Malaysia, Representatives from 11 government agencies, vets, academe etc. participating in both trainings (June-July 2022) PH: training will be conducted on January 2023

## Slide 7: Update on Workplan and Budget for 2022
Planned Activities | Time Frame | Budget (USD) | Remarks
To encourage CT6 participation in the regional Hammerhead Assessment supported by WWF and IUCN SSG | Q3-Q4 | Request RS to write again to IUCN | RS emailed on 15 June 2022 but yet to received any response
TRIPOD ongoing and scaling engagement: NCCs and RS to meet with TRIPOD partners to further explore opportunities for CTI-CFF to host and convene a regional taskforce and house TRIPOD toolkit for ongoing delivery and scaling to other CT countries If favorable, convene first taskforce meeting, post training. | Post SOM, likely a time between Jan-Mar 2022 In line with TRIPOD regional workshop or TS Working Group meeting | Funded by TRIPOD partners | Refer to partners update Regional Training probably conducted in February or March 2023, with contents and scope currently being agreed on by TRIPOD Partners, based on national CTOC and CCW training feedback The regional workshop will facilitate discussions between law enforcement officers from ID, MY, and the PH on and develop and/or review. Purposed location in ID

## Slide 8: Workplan and Propose Budget for 2023
Planned Activities | Time Frame | Budget (USD)
4th Threatened Species working group In-Situ Online Meeting Write-shops: (Postponed to 2024) • Draft the Framework plan for the Regional Conservation Plan | Q2 PH: Invitation 1-2 months prior the meeting | USD 8,500
Targeting Regional Investigations for Policing Opportunities & Development (TRIPOD) Project (ID, MY, PH): • Philippine government to participate in national Counter Transnational Organized Crime (CTOC) training • NCCs participate in regional workshop and involvement in the regional taskforce | Jan 2023 Feb/Mar 2023 | Funded by TRIPOD partners
TRIPOD ongoing and scaling engagement: • NCCs and RS to meet with TRIPOD partners to further explore opportunities for CTI CFF to host and convene a regional counter IWT taskforce with selected national focal points , and house TRIPOD toolkit for ongoing delivery and scaling to other CT countries, if favorable , convene first taskforce meeting post Training | Feb/Mar 2023 In line with TRIPOD regional event | Funded by TRIPOD partners
TRIPOD ongoing and scaling engagement: • CTI-CFF member States participate in the Asia Pacific Marine Turtle Genetic Working Group and contribute to ShellBank, in line with CITES turtle mandates, to collect DNA samples from wild and seized marine turtle specimens to determine species and geographic origin in support of research, investigations and prosecutions • CTI-CFF encourages member states to replicate the activities of the TRIPOD project after project closure in their countries and help disseminate the outputs of the project to inform national Legislation | On going, beyond project end Beyond project end | In part funded by ShellBank project Seek funding

## Slide 9: Workplan and Propose Budget for 2023 (Con.)
Planned Activities | Time Frame | Budget (USD)
Conduct workshops/webinars on threatened species and Develop annual updates on TS of CT Region (e.g CITES appendix) [Output A.2.1.1a: By 2023, a regional guide, campaign material tools and messages regarding threats to threatened species and on addressing the threats (e.g. marine pollution including marine debris, oil spill and Deep-Sea Tailing Disposal, and illegal fishing methods), are developed and distributed). Output A.2.2.1.b: By 2025, a regional campaign to combat illegal wildlife trade on priority threatened species (marine mammals, sea turtles, sharks and rays) is designed and implemented, as well as promoted, at national, regional and international levels Outcome A2.2.2: A reduction of the wildlife trade on priority threatened species (marine mammals, sea turtles, sharks and rays) is achieved] | Q2/Q3 | RS will further discuss with the partners for funding support
Develop CT Region Sea Turtles genetic database [Output A2.2.2.a: By 2030, illegal wildlife trade identified and monitored, focus on priority threatened species (marine mammals, sea turtles, sharks and rays), aligned with relevant CT6 national conservation or management plans] | Q3/Q4 | WWF currently looking into procuring funding for the ShellBank project, for developing the regional sea turtle genetic database. In case we'll be able to procure funding, then the activity may be implemented in 2023, therefore, we welcome "subject to funding availabilities".

## Slide 10: Recommendations for SOM 17
Acknowledged and appreciated the presentation by TS Working Group (Annex 1);
Encouraged the member countries to finish the National Assessment Report for Threatened Species on Sharks and Rays;
Encouraged CT6 to submit annual update on threatened species status in respective country and encourage RS to publish the compilation of the updates in CTI-CFF Website (Annex 2);
Agreed on the conduct of 4th Threatened Species working group meeting to be undertaken in 2023 through In-Situ online. Provided there is external funding support, a physical meeting might be held;
Acknowledged and appreciated the contribution of WWF through TRIPOD and SARRI project and agreed to incorporate the TRIPOD activities with the workplan 2023 (Annex 3a, 3b and 3c);
Noted the possible participation in the Asia Pacific Marine Turtle Genetic Working Group and contribute to ShellBank, in line with CITES turtle mandates, to collect DNA samples from wild and seized marine turtle specimens to determine species and geographic origin in support of research, investigations and prosecutions;
Encouraged member states to replicate the activities of the TRIPOD project after project closure in their countries and help disseminate the outputs of the project to inform national legislation;
Approved the TS Working Group 2023 Workplan