## Slide 1: Papua New Guinea
Ms. Kay Kalim
Director – Sustainable Environment Programs
Conservation and Environment Protection Authority
Head of Delegation
24 – 25 November 2022

## Slide 2
Outline
Members (Agencies) of the National Coordination Committee
Progress/Accomplishments towards NPOA Seascape, EAFM, MPA, CCA, Threatened Species, WLF and GESI Adoption
Challenges/Constraints Affecting Implementation
National Roadmap 2023 Seascape, EAFM, MPA, CCA, Threatened Species, WLF and GESI Adoption
Potential Regional Program and Support Required
Publications

## Slide 3
Conservation and Environment Protection Authority – Chair & Secretariat
National Fisheries Authority – Vice Chair
Climate Change and Development Authority
Department of Treasury
Department of National Planning and Monitoring
Department of Prime Minister and NEC
Department of Foreign Affairs
Department of Provincial and Local Level Government Affairs
National Oceans Office
National Maritime Safety Authority
University of Papua New Guinea
World Wildlife Fund
The Nature Conservation
Wildlife Conservation Society
Members of the National Coordination Committee

## Slide 4: Focal Points for Technical Working Groups
Working Group | Focal Point
Seascapes | Ms Yvonne Tio, Executive Manageress Marine, CEPA
Ecosystem Approach to Fisheries Management | Mr Thomas Usu, Executive Manager Fisheries- NFA
Marine Protected Areas | Mr Bernard Suruman, Manager Marine Protected Areas, CEPA
Threatened Species | Mr Vagi Rei, Manager, Marine Ecosystems, CEPA
Climate Change Adaptation | Mr Iki Peter, Senior Adaptation Officer, CCDA
Financial Resources Working Group | Mr Junior Hasu, Department of Treasury and Finance
Internal Resources Committee | Ms Nancy Kavu, Manager Revenue, CEPA

## Slide 5
PROGRESS TO DATE

## Slide 6: Seascape (supported through the RS)
Solutions for Marine and Coastal Resilience (SOMACORE) Project-Milne Bay Province and New Ireland Province
SOMACORE implementation start date January 2023.
Eco Custodian Advocates are the local PNG Implementing partner
Eco Custodian Advocates are building on the customary law (Gwala) and existing laws that support this approach to encourage sustainable fishery management for food, trade and income security, these laws are a fishery ‘conservation’ tool of closure that leads to ecological and stock recovery.

## Slide 7: Seascape (supported through partners)
Ridge to Reef Project in Milne Bay Province - Supported by the USAID- LGP in partnership with TNC
Ridge to Reef Assessment for Sustainable and Responsible Development- Integrated Provincial Development Plan
(Aligned to PNG Marine Program 2019 Target 2: Marine and Coastal Resources with priority seascapes sustainably managed Output 1.2.1.2 .b)

## Slide 8: Ecosystem Approach to Fisheries Management
ATSEA-2 PHASE II- South Fly District-Western Province
Establishment of;
Regional Governance Mechanism (RGM)
National Inter-Ministerial Committee (NIMC)
Stakeholder Partnership Forum (SPF)
Capacity building and training in EAFM principles carried out to CEPA and NFA officers and Western Provincial Fisheries officers and Representatives Torres Strait Treaty communities
1st Draft Artisanal Fisheries management plan developed for South Fly District Western Province

## Slide 9
Capacity Building
Regional Exchange on Oil Spill Preparedness and Response Training attended by NFA and NMSA.
Training Workshop on Improving Climate Awareness in the ATS Region attended by NFA and South Fly District Fisheries.
Mud Crab Fishery
Working with all 14 Maritime provinces (provincial fisheries officers) in the management of the mud crab fishery country wide.
Gazettal of the National Mud Crab Management Plan
Inshore Fish Aggregating Devices (IFAD) Program
Completed re-deployment of 15 IFADs in Manus, Madang, Morobe, AROB and East Sepik Provinces.
Ecosystem Approach to Fisheries Management - continued

## Slide 10: Marine Protected Areas
Documentation of Traditional Conservation practices in selected MPA sites, in 3 provinces, New Ireland Province, West New Britain and Milne Bay Province –production of short documentaries.
Continuation of Sustainable Livelihood projects for alternate sources of protein in Bootless Bay MPA through partnership with Kyeema foundation. Village chicken farming training
Production of a guideline on establishing a Conservation Deed, through partnership with USAID Lukautim Graun Project

## Slide 11: Marine Protected Area continued
Development of the marine protected area management plans-100 community consultations carried out to develop two site-specific management plans for Murat and Lavongai LLG in the New Ireland Province, through WCS with support from the Blue Action Fund
Enforcement of unregulated activities/illegal mangrove clearance in the Bootless Bay MPA through issuance of stop work notices
Conduct of plastic clean up and waste audits at selected sites

## Slide 12: Climate Change Adaptation
PACRES is supporting scaled up adaptation pilots including EAFM and food security in two provinces of PNG-Central and Gulf Province
Karama Village, Malalaua District, Gulf Province
Keapara, Alukuni & Karawa villages, in the Rigo District, Central Province
Pacific Adaptation to Climate Change and Resilience Building (PACRES) Project.

## Slide 13
Two maritime provinces have signed a Memorandum of Understanding(MoU) with Climate Change and Development Authority (CCDA) in Milne Bay and New Ireland Province to establish their Provincial Climate Change Committee (PCCC).
Climate Change Adaptation - continued

## Slide 14: Threatened Species
Sharks and Rays
National Plan of Action for Shark & Rays (2021-2024) funded by WWF under SPREP-BIEM-Implemented in 15 maritime provinces, NGO partners specifically Piku Biodiversity Network, WWF and WCS
Due for Review in 2023- schedules on Sawfish and Shark by catch to be included as well as an M&E and financing plan
Shark By catch in the Kikori Delta- Gulf Province, Photo Credit Piku Biodiversity Network 2022

## Slide 15: Threatened Species - continued
CITES Sharks Listing for PNG under Appendix 2
Proposal 37
Carcharhinidae spp.(Requiem sharks)
Grey reef shark (C. amblyrhynchos)
Sharptooth Lemon Shark (Negaprion acutidens)
Proposal 38
Sphyrnidae spp. (Hammerhead sharks)
Proposal 40
Rhinobatidae spp.(Guitarfishes)
Proposals listed were voted on by Parties and accepted as of 22/1/22 at the COP 19 in Panama

## Slide 16: Threatened Species
By catch project under Piku Biodiversity Network-Kikori Delta, Gulf Province
Assessment of Target and non target catch rates in the Kikori swim bladder fishery
Dolphin by-catch data collection and community engagement in Kikori River Delta and assess by-catch of threatened marine species by small-scale fishers and mitigation options in the Kikori River Delta, including shark and ray species as well as the dolphins in general
Shark By catch in the Kikori Delta- Gulf Province, Photo Credit Piku Biodiversity Network 2022

## Slide 17: Threatened Species
Marine Turtles
Revival of the Leatherback Turtle Monitoring Network in the Huon Gulf District, Morobe Province
Current data for leatherback turtle data to be put into the TS database (nesting data) migratory routes, status of nesting female population
Krill Market Survey, Market data collected for 2 provinces; Central and NCD to see if locals are sustainably trading Marine Turtles, Sharks and Rays and other indicator species
Nesting and Monitoring Data for Hawksbill and Green turtle from the Conflict Group of Islands, Milne Bay Province, collected by Conflict Islands Conservation Initiative

## Slide 18: Threatened Species
Outreach and Awareness
Threatened Species Awareness carried out in 5 provinces (Central , NCD, Gulf, Western, West Sepik) 20+ schools given TS materials, communities and stakeholders- over 1000 students reached. More awareness raised amongst students and public on importance of TS

## Slide 19: Progress – WLF and GESI Adoption
Signing of MOU with the Sea Women of Melanesia PNG
Forming of Networks with PNG Young women Leaders, Shifting the Power Coalition Hub (SPTC)
Focal point attended 1 disability workshop under Meri Gat Information Project
Mud crab project in Biotou village, Mekeo, Central Province-Exploring opportunities for women and people living with disabilities in the rural communities to earn an income from sustainable mud-crab harvesting- with funding from the Leprosy Foundation
Advocating for disability inclusion in conservation and climate change on a national level-WLF GESI Policy Adaptation

## Slide 21: Challenges
Funding shortfalls from National Government on the PNG Marine Program 2019-2023(NPOA) and partners
Delay in payment of Country Contributions to RS
Manpower shortage-Headquarters and provinces
Capacity building- (NCC training needed in resource mobilization)
Legislation and Policy- need to amend legislations, pass outstanding bills (Fauna Protection and Control Act, Protected Areas Bill)

## Slide 22
Review and develop the revised National Plan of Action-PNG Marine Program (2019-2023)- (2024-2028)

## Slide 23: Roadmap – Seascape
Ridge to Reefs Assessment for Sustainable and Responsible Development- Integrated Provincial Development Plan –Milne Bay Province
Marine Spatial Planning for Milne Bay Province
(Solutions for Coastal and Marine Resilience)SOMACORE Project implementation in New Ireland and Milne Bay Province

## Slide 24: Roadmap – EAFM Activities Related to CTI-CFF Goals with Different Budget
Endorsement of the Artisanal Fisheries Plan for South Fly by the Fisheries Board
Trans-boundary diagnostic analysis needs to be reviewed and prioritized
Reaffirm and strengthen the ATS relationship (Multi/bilateral policies- eg. Oceans Policy, National Protected Area Policy, Fisheries Policy)
EAFM training to be scaled out to other maritime provinces
Work closely with existing initiatives in South Fly District

## Slide 25: Roadmap – MPA
Hosting of the Marine Protected Area Regional Exchange (MPA REX)
Establishing 10 new LMMAs sites in 5 maritime provinces.
Establish 10 marine litter sampling sites in 10 LMMAs.
Conduct METT assessment for 10 existing LMMA/CCA.
Introduce & promote 2 sustainable livelihood options to 5 LMMA/CCA sites.

## Slide 26: Roadmap – CCA
Endorsement of the National Adaptation Plan (NAP) for PNG by the National Executive Council by the end of the year 2.
NAP implementation starting in 2023. Working with sectors to integrate CCA into sectoral plans and policies.

## Slide 27: Roadmap – Threatened Species
Conservation Management Plan for Threatened Species in PNG
Dugong & Marine Turtle National Plan of Action.
Review of National Plan of Action for Sharks and Rays to include schedules on Sawfish, By catch management , and Monitoring and Evaluation Framework
Legislation Reviews (Fauna Protection and Control Act, Conservation Areas Act)

## Slide 28: Roadmap –WLF and GESI Adoption
Leadership training and capacity building program for young women leaders planned for Q2 2023
Explore opportunities for youth empowerment in conservation, identify youth champions in the 15 maritime provinces, possibly develop MOU with the National Youth Development Authority (NYDA)
Support the UNDP Investing in Coral Reefs and the Blue Economy Project in empowering Women led SME’s in Kimbe Bay, West New Britain Province
Continue networking with People Living with Disabilities, for inclusion into PNG Marine Program Activities, possibly identify local champions and integrate their involvement with NGO’s.

## Slide 30: Potential Regional Program and Support Required
Capacity building
Technical Support
Facilitation of grant funding for Technical Working Groups to implement activities in the workplan
Production and design of Promotional Materials for the five technical working groups
Facilitate formal and informal learning for coastal communities and partner agencies towards successful management of Marine Resources

## Slide 32: Publications

## Slide 33: Publications