## Slide 1: Timor-Leste’s Report
By : NCC Timor-Leste

## Slide 2
Outline
Members (Agencies) of the National Coordination Committee
Progress/Accomplishments towards NPOA
Seascape, EAFM, MPA, CCA, Threatened Species, WLF and GESI Adoption
Challenges/Constraints Affecting Implementation
National Roadmap 2023
Seascape, EAFM, MPA, CCA, Threatened Species, WLF and GESI Adoption
Potential Regional Program and Support Required
Publications

## Slide 3: Members (Agencies) of the NCC
Working Group | Focal Point
Seascape | Focal Point : Mr. Fidelino Sousa Marques(Chief Cabinet of GDG-PARM) Alternate : Ms. Dominica Paula Geronimo Guterres (Technical Staff for Department of Marine Spatial Planning and Aquatic Resources Management) and Mr. Delio da Costa Technical Staff for the Department of R&D FOR Fisheries and Aquaculture)
EAFM | Focal Point : Mr. Timotio Alves (Technical Staff for Department of Capture and Post-Harvest) Alternate : Mr. Egidio Antonio Boavida (Technical Staff for Department of Marine Spatial Planning and Aquatic Resources Management)
MPA | Focal Point : Mr. Benvindo Maria de Deus Araujo dos Santos (Technical Staff for Department of Conservation Marine Biodiversity, and Aquatic Environment Management)
CCA | Focal Point : Mr. Rui dos Reis Pires (Nacional Director for Biodiversity) Secretary State of Environment
Threatened Species | Focal Point : Mr. Fernando da Silva (Technical Staff for Department of Conservation Marine Biodiversity, and Aquatic Environment Management) Alternate : Mr. Benvindo Maria de Deus Araujo dos Santos(Technical Staff for Department of Conservation Marine Biodiversity, and Aquatic Environment Management)
WLF | Focal Point : Mr. Alda Sousa Lemos da Rosa (Chief Department for RN of Fisheries And Aquaculture) Alternate : Mr. Esmeralda dos Santos ( Administrative Staff for GDG-PARM)

## Slide 5: Progress – Seascape CTI-CFF National Programs
CTI-CFF National Programs
Activities Related to CTI-CFF Goals with Different Budget
Trans boundary Diagnostic Analysis
SWG In-Situ online meeting was conducted on 31 October 2022 back-to-back with EAFM

## Slide 6: Progress – EAFM
Activities Related to CTI-CFF Goals with Different Budget
Capacity building for Fyber glass boat construction to the Fishermen
Seaweed Culture training for Conservation group and Fishermen
Training on upgraded sustainable fishing technologies for small scale fishers (Bottom-Long-Line) to Fishermen/women groups
Ecosystem Approach to Fisheries Management and Ecosystem Approach to Aquaculture
Consultation on providing value chain function of fishermen
Capacity building on Seafood Processing.
Increase the dimension concept capacity of coastal integrity management for fishers group
CTI-CFF National Programs
EAFM WG In-Situ online meeting was conducted on 31 October 2022 back-to-back with SWG

## Slide 7: Progress – EAFM - Continuation
Activities Related to CTI-CFF Goals with Different Budget
Survey on Value Chain/Supply chain and Fish consumption
Capacity building on Conservation group, Fishermen and Coastal Communities regarding EAFM plan
Seaweed Diversification Product for gender group
Dissemination Laws and Regulations of Fisheries
Survey on process of value chain and availability facilities
Strengthening EAFM curriculum in two Universities
Community Meeting, Development of Plan and monitoring phase Ecosystem Approach to Fishery Management (EAFM) Management Plan

## Slide 8: Progress – EAFM-Continuation
Activities Related to CTI-CFF Goals with Different Budget
Fishing Boat Marking
Capacity building on Conservation group, Fishermen and Coastal Communities regarding EAFM plan
Rumpon(FAD) Construction
Establishment of Fisheries Advisory Committee
Sanitation, Hygiene and Engagement with the Coastal Communities and Professional Staff for Fish Handling

## Slide 9: Progress – MPA
CTI-CFF National Programs
Activities Related to CTI-CFF Goals with Different Budget
Marine Habitat Management Review on the North Coast of Timor-Leste
New establishment of LMMA in Behau and Beto tasi pilot sites
Capacity building on Line Intercept Transect (LITs) method for conservation group
Establishment of Marine Networking
Reef Check Training
Establishment of the New MPA in Southern part of Timor-Leste
MPA Management in North Coast of Timor-Leste
Regular Monitoring on the new establishment MPA
1. MPA WG In-Situ online meeting was conducted on 11 Nov 2022
2. CT Atlas Training conducted on 28 October 2022
3. II Learning Exchange Workshop on the Ocean Governance project on 12-14 October 2022 in Kota Kinabalu,

## Slide 10: Progress – CCA
CTI-CFF National Programs
Activities Related to CTI-CFF Goals with Different Budget
Green School
Carbone Capture
Zero plastic Policy
Mangrove reforestation
Ikan Adapt
Reforestation activities
Capacity Building on Natural Resources Management
Oil Spill Training Preparedness
CCA WG In-situ online Meeting was conducted on 27 Oct 2022

## Slide 11: Progress – CCA-Continuation
Activities Related to CTI-CFF Goals with Different Budget
Weekly cleaning program every Friday to all of the Public servants
School campaign regarding the responsible of plastic used
Capacity Building on Up Recycling techniques training
Climate Change Vulnerability Assessment

## Slide 12: Progress – Threatened Species
CTI-CFF National Programs
Activities Related to CTI-CFF Goals with Different Budget
Formulation of the Guideline books regarding the Cetaceans to the Primary school
Joint Diploma Ministerial No.18/MAP/MCIA/II/2017 in reference from CITES to protect threatening aquatic species
Educational Campaign
Regular Monitoring to the Turtle Path and its Nesting side
Education Campaign to Coastal Communities and Primary School on Endangered Species.
Establishment of Drought Resilient home gardens
Threatening Species Working group In-Situ online Meeting

## Slide 13: Progress – WLF and GESI Adoption
Seaweed Diversification Product for Gender Group
Rural Women activities regarding the Woman Empowerment
Second phase of Ministry of Agriculture and Fisheries GESI policy Political regarding the women have the rights inclusion in all activities and positions.
Women desegregate Data collection
Share commitment with the maritime Woman regarding human trafficking in Timor-Leste

## Slide 15: Challenges
1. Timor-Leste with the limited resources is facing a lot of challenges, issues and constraints during the progress achieving the National Plan of Actions are as follow:
Limited resources/expertise
Knowledge gaps
Financial resources
2. Limited of communication between stakeholders
Limited communication among stakeholders in implementing and achieving CTI-CFF programs and goals. The focal points and technical working groups of CTI-CFF in Timor-Leste were not involved in most of the programmes and funds under of CTI-CFF programs. Hence, the TWG and focal points had limited information of the programmes and activities which are directly under the CTI-CFF programs.

## Slide 16
3. IUU-Fishing due to Limited of Enforcement
4. The pandemic of COVID19 in Timor-Leste
The pandemic of COVID19 is the big challenge of all over the world and the CT6 member’s country. Likewise in Timor-Leste, the pandemic COVID19 had been the major challenges in Timor-Leste during 2020 till 2021. The government of Timor-Leste, included the Ministry of Agriculture and Fisheries, development partners and agencies has to suspend stop most of their programs and activities.
Challenges-Continuation

## Slide 18: Roadmap – Seascape
Activities Related to CTI-CFF Goals with Different Budget
1. Marine Spatial Planning for Timor-Leste
2. Marine Rapid Assessment in the area of Laser Sunda Seascape to contribute to the Nature Peace Park Initiative of Timor-Leste
1. 7th Seascape Working Group Meeting together with Seascapes Working Group Regional Exchange
CTI-CFF National Programs

## Slide 19: Roadmap – EAFM
1. Construction of the Industrial ship Logline and Gillnet
2. Distribution of the 110 Pieces of the small scale boats to the Fishermen
3. Provide additional technical support towards the implementation activities against IUU and complement the implementation of the NPoA
4. Capacity building on the concept and Dimension on Integrated Coastal Managements
Activities Related to CTI-CFF Goals with Different Budget
CTI-CFF National Programs
1. 8th EAFM Working Group Meeting together with Seascapes Working Group and discussion workshop on the RPOA 2.0 targets, regional activities.

## Slide 20: Roadmap – MPA
1. ATSEA phase 2 program in the South Coast of Timor-Leste will expand its MPAs to Ainaro and Covalima Municipalities to complete the 90.000 ha based on TOR.
2. Capacity building training program on marine ecological assessment such as fish stock assessment, monitoring and evaluation tracking tools for MPAs.
3. Strengthening the adaptive capacity, resilience and biodiversity conservation ability of fisheries and aquaculture-dependent livelihoods in Timor-Leste in collaboration with the Minderoo Foundation and Ministry of Agriculture and Fisheries.
4. Launch the Tara Bandu on Protected Conservation Area
Activities Related to CTI-CFF Goals with Different Budget
CTI-CFF National Programs
1. 9th MPA REX and 9th MPA TWG Meeting in 2023 through In-Situ online
2. CTMPAS 3rd Round of Nomination for Categories 3 and 4, and the Award for Categories 1 to 4

## Slide 21: Roadmap – CCA
1. Develop of a Pollution Prevention and Control plan as part of the activities.
Activities Related to CTI-CFF Goals with Different Budget
CTI-CFF National Programs
1. 7th CCA Working Group Meeting together with Regional Exchange: Developing CEPA and Strategy for CCA

## Slide 22: Roadmap – Threatened Species
1. Waiting for the approval and ratification for the Joint Diploma Ministerial in reference from CITES to Cetaceans Watch activities.
2. Identification Potential Areas for Management of Fisheries Resources (Turtle Nesting sites)
3. Construction of the conservation centre to preserve and manage the turtle egg and its nesting sites.
Activities Related to CTI-CFF Goals with Different Budget
1. 4th Threatened Species working group In-Situ Online Meeting
CTI-CFF National Programs

## Slide 23: Roadmap –WLF and GESI Adoption
1. Continuation of the Women desegregate Data Collection.
2. Capacity Building for Woman as empowerment to all Cross cutting activities.
CTI-CFF National Programs

## Slide 25: Potential Regional Program and Support Required
1. The revision of NPOA of Timor-Leste will require the support from the Regional Secretariat.
2. Capacity Building and Learning exchange between countries to enhance their knowledge and skill.

## Slide 27: Publications
Nutrition Baseline Survey (Worlfish TL 2022).
Stock assessment and value chain assessment of the red snapper fishery in South Coast of Timor-Leste (ATSEA Phase 2 Project 2022).
Notes: Most of the publication extended to 2023